## Project Cost Tracker
PROJECT COST TRACKER — Budget vs Actual & Milestone Billing
Free template from Fast Project Management Software (www.fastprojectsoftware.com) — for engineer-to-order, EPC, fabrication & construction projects. Rows below marked 'SAMPLE' are examples — delete them and enter your own.
Project: | ________________ | Project Code: | __________ | Customer: | ________________ | Owner: | __________ | Currency: | INR (₹)
WBS / Task | Description | Budgeted Cost | Actual Cost | Variance | Resource | Start | End | % Complete | Billing Milestone
SAMPLE — 1.0 Engineering & Design | Detailed drawings, GA & BOM release | 120000 | 118500 |  | Design Engineer | 2026-08-01 | 2026-08-10 | 100% | Milestone 1 – Design sign-off (20%)
SAMPLE — 2.0 Procurement | Plate, sections & bought-out items | 480000 | 512000 |  | Purchase / Stores | 2026-08-11 | 2026-08-25 | 100% | Milestone 2 – Material at works (30%)
SAMPLE — 3.0 Fabrication | Cutting, fit-up & welding of assembly | 360000 | 344000 |  | Fabrication Shop | 2026-08-26 | 2026-09-15 | 80% | Milestone 3 – Fabrication complete (25%)
SAMPLE — 4.0 Surface & Assembly | Blasting, painting & final assembly | 145000 | 96000 |  | Paint + Assembly | 2026-09-16 | 2026-09-24 | 45% | Milestone 4 – Ready for inspection (15%)
SAMPLE — 5.0 Inspection & Dispatch | QA, documentation & despatch to site | 75000 | 0 |  | QA / Logistics | 2026-09-25 | 2026-09-30 | 0% | Milestone 5 – Dispatch / final bill (10%)
TOTAL | Project budget vs actual
How to use: 1) Delete the SAMPLE rows. 2) Enter your WBS tasks, budgeted & actual cost — Variance (Budget − Actual) calculates automatically. 3) Track % Complete and tag each task to a billing milestone (advance / material-at-site / progress / RA / final). Want this linked to live store issues, cost estimation and milestone bills automatically? See Fast Project Management — www.fastprojectsoftware.com